## Team Info
Team Name
TEAM MEMBERS | Role | Name | Mail Address
| Scrum Master | Imane Koulali | imane.koulali@isikun.edu.tr
| Product Owner | Cahit Çokal | cahit.cokal@isikun.edu.tr
Development Team Member
Product | Company - HR Application
Technologies | Web Application - Front End Texh.: React - Back End Tech.: node .js - Database Tech.: mySQL
Laboratory Time Slot | Thursday / 18:30-18:50
Product Vision | Our vision is to develop an user-friendly HR application that simplifies and facilitate HR management for businesses of all sizes.
Product Goals | Streamline HR processes to reduce administrative works.
Provide data-driven understanding through graphs and analytics
Document management capabilities by providing features to categorize, upload, download, and delete documents.
The system will ensure compliance with HR regulations and policies by implementing secure authentication
DoD | All the acceptance criteria must be met.
All the defects should be fixed.
All the functionality must be tested.
Necessary documents (RAD, SDD, ODD) must be updated accordingly.
Trello Board

## Epic List
ID | Title | Description
1 | Security(Login,Register etc.) | HR Team can log in, log out, and reset passwords, New members of the HR application can register the system.
2 | Administration
3 | Search Emloyee | Admin can manage user accounts, roles, permissions, and view audit logs of system.
4 | Employee Details | HR Team can search for employees by name, department, or other criteria, with results displayed.
5 | Payroll | HR Team can view detailed employee information.
6 | Performance | HR Team can access and manage employee salaries, bonuses, and deductions.
7 | Data Virtualization | HR Team can view performance metrics and manage performance reviews.
8 | Authentication | HR Team can display graphs with data from the database.
9 | Associate Modification | Logging to the system will be secured by an authentication.

## PBIList
Epic ID | Epic Title | User Story Title | User Story Description | Estimation | State | Sprint | Emerged?
1 | Security(Login,Register etc.) | Login ¦ Administrator Login | As an admin user I would like to log in to the system such that I can start to manage the HR Teams, employees and their details. Acceptance Criteria: * Admin users will be created in database manually with "system admin" role. * Admin user will enter their username. * Admin user will enter their password. * Admin user will click Login buton. * Admin user will be redirected to the home page if succesfully logged in. * Admin user will be warned via an error message if log in is unsuccesfull. | 8 | Done | 1 | FALSE
2 | Administration | Company Admin ¦ Administration Dashboard Page. | As a company admin user I would like to be able to see important information on my home page as a dashboard such that I will be able to see summary details related to important activities and notifications. Acceptance Criteria: * Company admin will see all the company employees in a box on home/dashboard page. - Company admin will see the number of active employees of the company. - Company admin will see the number of inactive employees of the company. * Company admin will see the number of HR Team Members created in HR Team Members box. - Company admin will see the number of active HR Team Members in HR Team Members box. - Company admin will see "Manage HR Team Members" button at the bottom of the company users box. * Company admin will see a button to go to the Company Detail Page. | 13 | Done | 1 | FALSE
1 | Security(Login,Register etc.) | Login ¦ Logout | As a HR Team Member I would like to logout from the system such that I can securely leave the system after finishing my discovery. Acceptance Criteria: * User will click on Logout Link/Button. * User will be redirected to login page. | 5 | Done | 1 | FALSE
2 | Administration | Company Admin ¦ Company Detail Page | As a company admin user I would like to be able to see the details of a companies after clicking on the row from the list of companies. Acceptance Criteria: * Company admin will click on "View Company Details" button from Dashboard Page. * Company Detail Page will be displayed including all the information of the company including "Activation Date" and "Company Status". * An action button "Update Information" will be at the bottom of the detail page. * Company admin will be able to update teh company information by clicking this button. | 8 | Done | 2 | FALSE
2 | Administration | Company Admin ¦ Company Update Page | As a company admin user I would like to be able to update the details of a companies after clicking on the "Update Information" button from the Company Details Page. Acceptance Criteria: * Company admin will click on "Update Information" button from Company Details Page. * Company Information Update Page will be displayed including all the information of the company. * Company admin will click on "Save" button after completing the edit. * The information will be stored to database and "Last Action Date" will be updated as system date. * In any error case, company admin will be warned. | 13 | Done | 2 | FALSE
2 | Administration | Company Admin ¦ List HR Team Members | As a company admin user I would like to be able to see the list of all the HR Team Members with summary information table after clicking on "Manage HR Team Members" button from dashboard. Acceptance Criteria: * System admin will click on "Manage HR Team Members" button from dashboard. * All the company users will be listed as a table with below columns. - Creation Date - First Name - Last Name - Status (Active/Blocked) * The HR Team Members will be listed from newest to the oldest according to the "Creation Date". * There will be pagination in the listing page with max 20 per page. * There will be "Add New HR Team Member" button at the top of the user list. The company admin will be able to create new HR Team Members with this button. | 8 | Done | 2 | FALSE
2 | Administration | Company Admin ¦ HR Team Member Detail Page | As a company admin user I would like to be able to see the details of HR Team Members by clicking on the row from the list of HR Team Members. * Company admin will click on "View HR Team Member Details" button from HR Team Member Listing Page. * HR Team Member Detail Page will be displayed including all the information of the member including "Create Date" and "Status". * An action button "Update Information" will be at the bottom of the detail page. * Company admin will be able to update the HR Team Member information by clicking this button. * An action button "Block User" will be at the bottom of the detail page. * Company admin will be able to block the HR Team Member by clicking this button. | 8 | Done | 3 | FALSE
2 | Administration | Company Admin ¦ Add a New HR Team Member | As a company HR Team Member I would like to be able to create a new HR Team Member such that they will be able to log in to the system and start to manage the employees and their details. Acceptance Criteria: * Company admin will click on "Add New HR Team Member" button on List of HR Team Members Page. * Department will be "HR Team" by default and cannot be changed (Mandatory). * Company admin will enter First Name (Mandatory). * Company admin will enter Last Name (Mandatory). * Company admin will enter Birth Date (Mandatory). * Company admin will enter Birth Place/Country (Mandatory). * Company admin will enter Birth Place/City (Mandatory). * Company admin will select Gender (Mandatory). * Company admin will enter address information (Can be freetext) (Optional). * Company admin will enter Phone Number (Optional). * Company admin will enter email (Mandatory). * Company admin will click "Create" buton. * Company admin will be warned via error message if mandatory fields are missing or not valid (eg. email). * HR Team Member will receive an email with a link to create password page. * HR Team Member will enter his/her password two times. * HR Team Member will be redirected to the login page if succesfully create password, and be forced to log in with new password. * HR Team Member will be warned via an error message if passwords are not matched. * Username will be the email. * HR Team Members will be created in database automatically after succesfull register progress with "hr team member" role. The "Creation Date" will be the system date and the status will be "Active". | 21 | Done | 3 | FALSE
2 | Administration | Company Admin ¦ Block an Existing HR Team Member | As a company admin user I would like to be able to "Block" a HR Team Member by clicking on the "Block" button in HR Team Member Detail Page Acceptance Criteria: * Company admin will click on "Block" button in HR Team Member Detail Page. * The system will change the HR Team Member status to "Blocked" and "Last Action Date" with system date. * HR Team Member will not be able to Login In to the system. * HR Team Member will see error message related to the status. | 13 | Done | 3 | FALSE
2 | Administration | Company Admin ¦ Unblock an Existing HR Team Member | As a company admin user I would like to be able to "Unblock" a HR Team Member user by clicking on the "Unblock" button in HR Team Member Detail Page Acceptance Criteria: * System admin will click on "Unblock" button in HR Team Member Detail Page. * The system will change the HR Team Member status to "Active" and "Last Action Date" with system date. * HR Team Member will be able to Login In to the system. | 13 | Done | 3 | FALSE
2 | Administration | Company Admin ¦ Update an Existing HR Team Member | As a company admin user I would like to be able to update the details of a HR Team Member after clicking on the "Update Information" button from the HR Team Member Details Page. Acceptance Criteria: * Company admin will click on "Update Information" button from HR Team Member Details Page. * HR Team Member Information Update Page will be displayed including all the information of the HR Team Member including "Activation Date" and "Status". * All the informaiton except "Status" and "Create Date" will be editable. * Company admin will click on "Save" button after completing the edit. * The information will be stored to database and "Last Action Date" will be updated as system date. * In any error case, company admin will be warned. |  | Approved | Backlog | FALSE
1 | Security(Login,Register etc.) | Login ¦ HR Team Member Login | As an HR Team Member I would like to log in to the system such that I can start to manage my company employees and their details. Acceptance Criteria: * Company users will enter their username. * Company users will enter their password. * Company users will click Login buton. * Company users will be redirected to the home page if succesfully logged in. * Company users will be warned via an error message if log in is unsuccesfull. |  | Removed | Backlog | FALSE
2 | Administration | HR Team Member ¦ Administration Dashboard Page. | As an HR Team Member I would like to be able to see important information on my home page as a dashboard such that I will be able to see summary details related to important activities and notifications. Acceptance Criteria: * HR Team Member will see all the company employees in a box on home/dashboard page. - HR Team Member will see the number of active employees of the company. - HR Team Member will see the number of inactive employees of the company. - HR Team Member will see "Manage Employees" button at the bottom of the company employees box. |  | Removed | Backlog | FALSE
4 | Employee Details | HR Team Member ¦ List Company Employees | As an HR Team Member user I would like to be able to see the list of all the company employees with summary information table after clicking on "Manage Employees" button from dashboard. Acceptance Criteria: * System admin will click on "Manage Employees" button from dashboard. * All the company users will be listed as a table with below columns. - Creation Date - First Name - Last Name - Status (Active/Blocked) * The employees will be listed from newest to the oldest according to the "Creation Date". * There will be pagination in the listing page with max 20 per page. * There will be "Add New Employee" button at the top of the user list. The HR Team Member will be able to create new employees with this button. |  | Removed | Backlog | FALSE
4 | Employee Details | HR Team Member ¦ Employee Detail Page | As an HR Team Member I would like to be able to see the details of employees clicking on the row from the list of employees. * HR Team Member will click on "View Employee Details" button from Company User Listing Page. * Employee Detail Page will be displayed including all the information of the user including "Create Date" and "Status". * An action button "Update Information" will be at the bottom of the detail page. * HR Team Member will be able to update the employee information by clicking this button. * An action button "Block Employee" will be at the bottom of the detail page. * HR Team Member will be able to block the employee by clicking this button. |  | Removed | Backlog | FALSE
4 | Employee Details | HR Team Member ¦ Add a New Employee | As an HR Team Member I would like to be able to create a new employee such that they will be able to log in to the system and start to manage the company products and their details. Acceptance Criteria: * HR Team Member will click on "Add New Employee" button on List of Employees Page. * HR Team Member will select the Department (Mandatory). * HR Team Member will enter First Name (Mandatory). * HR Team Member will enter Last Name (Mandatory). * HR Team Member will enter Birth Date (Mandatory). * HR Team Member will enter Birth Place/Country (Mandatory). * HR Team Member will enter Birth Place/City (Mandatory). * HR Team Member will select Gender (Mandatory). * HR Team Member will enter address information (Can be freetext) (Optional). * HR Team Member will enter Phone Number (Optional). * HR Team Member will enter email (Mandatory). * HR Team Member will click "Create" buton. * HR Team Member will be warned via error message if mandatory fields are missing or not valid (eg. email). * Employee will receive an email with a link to create password page. * Employee will enter his password two times. * Employee will be redirected to the login page if succesfully create password, and be forced to log in with new password. * Employee will be warned via an error message if passwords are not matched. * Username will be the email. * Employees will be created in database automatically after succesfull register progress with "employee" role. The "Creation Date" will be the system date and the status will be "Active". |  | Approved | Backlog | FALSE
4 | Employee Details | HR Team Member ¦ Block an Existing Employee | As an HR Team Member I would like to be able to "Block" an employee by clicking on the "Block" button in Employee Detail Page Acceptance Criteria: * HR Team Member will click on "Block" button in Employee Detail Page. * The system will change the employee status to "Blocked" and "Last Action Date" with system date. * Employee will not be able to Login In to the system. * Employee will see error message related to the status. |  | Approved | Backlog | FALSE
4 | Employee Details | HR Team Member ¦ Unblock an Existing Employee | As an HR Team Member I would like to be able to "Unblock" an employee by clicking on the "Unblock" button in Employee Detail Page Acceptance Criteria: * HR Team Member will click on "Unblock" button in Employee Detail Page. * The system will change the company user status to "Active" and "Last Action Date" with system date. * Employee will be able to Login In to the system. |  | Approved | Backlog | FALSE
4 | Employee Details | HR Team Member ¦ Update an Existing Employee | As an HR Team Member I would like to be able to update the details of an employee after clicking on the "Update Information" button from the Employee Details Page. Acceptance Criteria: * HR Team Member will click on "Update Information" button from Employee Details Page. * Employee Information Update Page will be displayed including all the information of the employee including "Activation Date" and "Status". * All the information except "Status" and "Create Date" will be editable. * HR Team Member will click on "Save" button after completing the edit. * The information will be stored to database and "Last Action Date" will be updated as system date. * In any error case, HR Team Member will be warned. |  | Approved | Backlog | FALSE
1 | Security(Login,Register etc.) | Login ¦ Company Employee Login | As an employee I would like to log in to the system such that I can start to manage my company products and their details. Acceptance Criteria: * Employee will enter their username. * Employee will enter their password. * Employee will click Login buton. * Employee will be redirected to the home page if succesfully logged in. * Employee will be warned via an error message if log in is unsuccesfull. |  | Removed | Backlog | FALSE
1 | Security(Login,Register etc.) | Login ¦ Forgot Password | As a user I would like to set a new password when I forget my password such that I will be able to log into the system again. Acceptance Criteria: * User will click on Forgot Password Link/Button. * User will be redirected to Forgot Password Page. * User will enter his/her email and click on submit button. * User will receive an email with a link to create password page. * User will enter his password two times. * User will be redirected to the login page if succesfully changed password, and be forced to log in with new password. * User will be warned via an error message if passwords are not matched. |  | Approved | Backlog | FALSE
1 | Security(Login,Register etc.) | Login ¦ User Profile Page | As a user I would like to see my user profile page when I click on User Detals Link / Button on top right of home page such that I will be able to see my user detail and reset my password. Acceptance Criteria: * User will click on icon on top right corener of the home page. * User will be redirected to User Profile Page. * System will display user information and Reset My Password Link. |  | Approved | Backlog | FALSE
1 | Security(Login,Register etc.) | Login ¦ Reset Password | As a user I would like to be able to change my password from User Profile Page when I logged in such that I can secure my profile. Acceptance Criteria: * User will click on Reset My Password button to set a new password. * User will enter a new password two times. * Users are redirected to the User Detail Page if succesfully changed the password. * Users are warned via error message if passwords do not match. |  | Approved | Backlog | FALSE
| #N/A | User Story 9 | Description of User Story 9 |  | New | Backlog | FALSE
| #N/A | User Story 10 | Description of User Story 10 |  | New | Backlog | FALSE
| #N/A | User Story 11 | Description of User Story 11 |  | New | Backlog | FALSE
| #N/A | User Story 12 | Description of User Story 12 |  | New | Backlog | FALSE
| #N/A | User Story 13 | Description of User Story 13 |  | New | Backlog | FALSE
| #N/A | User Story 14 | Description of User Story 14 |  | New | Backlog | FALSE
| #N/A | User Story 15 | Description of User Story 15 |  | New | Backlog | FALSE
| #N/A | User Story 16 | Description of User Story 16 |  | New | Backlog | FALSE
| #N/A | User Story 17 | Description of User Story 17 |  | New | Backlog | FALSE
| #N/A | User Story 18 | Description of User Story 18 |  | New | Backlog | FALSE
| #N/A | User Story 19 | Description of User Story 19 |  | New | Backlog | FALSE
| #N/A | User Story 20 | Description of User Story 20 |  | New | Backlog | FALSE
| #N/A | User Story 21 | Description of User Story 21 |  | New | Backlog | FALSE
| #N/A | User Story 22 | Description of User Story 22 |  | New | Backlog | FALSE
| #N/A | User Story 23 | Description of User Story 23 |  | New | Backlog | FALSE
| #N/A | User Story 24 | Description of User Story 24 |  | New | Backlog | FALSE
| #N/A | User Story 25 | Description of User Story 25 |  | New | Backlog | FALSE
| #N/A | User Story 26 | Description of User Story 26 |  | New | Backlog | FALSE
| #N/A | User Story 27 | Description of User Story 27 |  | New | Backlog | FALSE
| #N/A | User Story 28 | Description of User Story 28 |  | New | Backlog | FALSE
| #N/A | User Story 29 | Description of User Story 29 |  | New | Backlog | FALSE
| #N/A | User Story 30 | Description of User Story 30 |  | New | Backlog | FALSE
| #N/A | User Story 31 | Description of User Story 31 |  | New | Backlog | FALSE
| #N/A | User Story 32 | Description of User Story 32 |  | New | Backlog | FALSE
| #N/A | User Story 33 | Description of User Story 33 |  | New | Backlog | FALSE
| #N/A | User Story 34 | Description of User Story 34 |  | New | Backlog | FALSE
| #N/A | User Story 35 | Description of User Story 35 |  | New | Backlog | FALSE
| #N/A | User Story 36 | Description of User Story 36 |  | New | Backlog | FALSE
| #N/A | User Story 37 | Description of User Story 37 |  | New | Backlog | FALSE
| #N/A | User Story 38 | Description of User Story 38 |  | New | Backlog | FALSE
| #N/A | User Story 39 | Description of User Story 39 |  | New | Backlog | FALSE

## SprintMetrics
SPRINT | PLANNED |  | EMERGED |  | DONE |  | TOTAL |  | RATIO |  |  | SPRINT TEXT
| PBI | SP | PBI | SP | PBI | SP | PBI | SP | DONE/PLANNED | EMERGED/PLANNED | DONE/TOTAL
1 | 3 | 26 | 0 | 0 | 3 | 26 | 3 | 26 | 100 | 0 | 100 | Sprint 1
2 | 3 | 29 | 0 | 0 | 3 | 29 | 3 | 29 | 100 | 0 | 100 | Sprint 2
3 | 4 | 55 | 0 | 0 | 4 | 55 | 4 | 55 | 100 | 0 | 100 | Sprint 3

## Sprint Info
Sprint Number | Start Date | End Date | Sprint Goal
Backlog | . | . | .
3 | 2024-04-18 | 2024-05-02 | Admin user will be able to list the details of HR Team Member and also create a new HR Team Member in the system. Admin user will be able to block and unblock HR team members.
2 | 2024-04-04 | 2024-04-18 | Company information will be visible and editable.
1 | 2024-03-21 | 2024-04-04 | Admin user will be able to start to use the system with login, logout and see home page.
Formulas:
Start Date = [End Date, row below]
End Date = 'Sprint Info'!$[Start Date]+14

## Values
Emerged? | Work Item Category | Story Point | Work Type | Status
TRUE | Product | 0 | Feature | New
FALSE | Support | 1 | Bug | Planned
| Project | 2 |  | Approved
| Presales | 3 |  | Done
| Other | 5 |  | Removed
8
13
21
34
55
89
100

## Sprint 1
Team 1 Name - Sprint 1 Report
Trello Workspace URL
Sprint Goal
Sprint Backlog
Epic Number | Epic Title | Story Title | Description | Estimation | Status

## Sprint 2
Team 1 Name - Sprint 2 Report
Trello Workspace URL
Sprint Goal
Sprint Backlog
Epic Number | Epic Title | Story Title | Description | Estimation | Status

## Sprint 3
Team 1 Name - Sprint 3 Report
Trello Workspace URL
Sprint Goal
Sprint Backlog
Epic Number | Epic Title | Story Title | Description | Estimation | Status

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | 13
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_d.MM.yyyy HH:mm | readOnlyTestRange_General